## Intro
4th Year Software Test Plan
Project Name | Login Console
Project Manager | Naomi Hurley
Prepared by | Naomi Hurley and the 4th year Computing students
Tech Lead | To be confirmed
Date
Revision History
Revision | Author | Comment
1 | Naomi Hurley | Initial Draft

## Product No 1 or Sprint No 1
|  | Purpose: | This set of tests is intended to check main functionality developed
Till Application Neil Byrne - G00343624 Sean O'Gorman - G00314259 Matthew Bartley - G00342591 |  |  |  | Visual Studio 2017
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Expected Result | Actual Result | Results Pass/Fail | Bug # | Comments
1 | 1 | TC.001 | Login Credentinals | GUI | 1. Launch Application 2. Press "Food" button | User will be denied access | User will be denied access | Display message "Login to be able to use this feature" and user is denied access | Pass
2 | 1 | TC.002 | Login Credentinals | GUI | 1. Launch Application 2. Enter user ID "11111" 3. Press "Food" button 4. Go back to Main Page 5. Press "Logout" button 6. Press Food button | User "Neil Byrne" is logged in and out | User "Neil Byrne" will be logged in and given access then loses access when logged out | User "Neil Byrne" will be logged in and given access then loses access when logged out | Pass
2.1 | 1 | TC.0021 | Login Credentinals | GUI | 1. Launch Application 2. Enter user ID "11111" 3. Press "Food" button | User is brought back to main page after successful purchase | User "Neil Byrne" will be logged in and given access | User "Neil Byrne" is logged and and given access | Pass
3 | 1 | TC.003 | Cart | GUI | 1. Repeat previous test 2. Add "Beef" and "Broccoli Pasta" to cart 3. Press Checkout 4. Enter the correct amount 5. Finalize the order | In checkout total is displayed at 35 | Purchase is successful and user is brought back to main page | Purchase is successful and user is brought back to main page | Pass
4 | 1 | TC.004 | Cart | GUI | 1. Repeat ID 3.00 steps 1-3 2. Enter 40 (higher amount) | Check that user is given correct change | User is promted with 5 change required | The user is promted with a 5 change require and brought back to main page | Pass
5 | 1 | TC.005 | Cart | GUI | 1. Repeat ID 3.00 steps 1-3 2. Enter 30 (lower amount) | Error message displayed for Incificient funds | Error messaged displayed for Incificient funds | Error message displayed for Incificient funds | Pass
6 | 1 | TC.006 | Cart | GUI | 1. Repeat ID 2.00 steps 1-2 2. Press Checkout 3. Press Finalize order | Error message validation | Error message displayed "No items in cart" | Unhanled exception is thrown | Fail | Bug #1713-280419 | To be assigned

## Product No 2 or Sprint No 2
|  | Purpose: | This set of tests is intended to check main functionality developed
Test Run Title e.g. Login validation |  |  |  | Microsoft Internet Explorer 9 Windows 7 Microsoft Internet Explorer 10 Windows 7 Micresoft Internet Explorer 11 Windows 7 Microsoft Internet Explorer 8 Windows XP Microsoft Internet Explorer 7 Windows XP Firefox latest version Apple Safari Windows XP Apple Safari Google Chrome Windows XP Opera Windows XP
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Results Pass/Fail | Bug # | Comments

## Test Progress
Tabs | Developped by | No of test cases | Tester | No of days | Browsers | Test cases passed | Test cases failed | To be done | Percentage done
Sprint No
Test Run description | Team A | 18 |  |  | All | 0 | 0 | 18 | 0%
Test Run description | Team B | 8 |  |  | N/A | 0 | 0 | 8 | 0%
Test Run description | Team C | 19 |  |  | All | 0 | 0 | 19 | 0%
Test Run description | Team D | 20 |  |  | All | 0 | 0 | 20 | 0%
Test Run description | Team C | 42 |  |  | All | 0 | 0 | 42 | 0%
Total |  | 107 |  |  |  |  | 0 | 0 | 0%